## Read me
Early Warning Register
A free template from Clause 60 (clause60.com). Version 1.2, September 2026.
What it is for
NEC4 calls this document the Early Warning Register. NEC3 calls it the Risk Register. Both are a record of the matters notified as early warnings, plus any listed in the Contract Data, and of what was decided about each of them.
Under NEC4 the Project Manager prepares the first register and issues it within one week of the starting date, holds the first meeting no later than two weeks after the starting date, and reissues the register within a week of each meeting. Later meetings are held at the interval stated in the Contract Data. NEC3 has no equivalent fixed timetable. Check your own contract for all of these.
How to use it
1. Enter one matter per row on the Register sheet. Fill in the yellow cells. Grey cells are calculated.
2. In the "Could affect" columns, mark with an X each effect the matter could have. These columns follow the grounds on which an early warning is required.
3. Record what was decided at the early warning meeting, who is to act, and by when. The register shows the days left for each open action.
4. If the matter later becomes a compensation event, enter the compensation event reference. That link matters: if the Project Manager says the Contractor failed to warn of something it ought to have warned of, the assessment proceeds on the footing that the warning was given on time.
5. Row 5 is an example. Overwrite or clear it when you start.
The register is not the early warning
Adding a line to this register is not the same as giving an early warning. The contract requires the early warning to be notified as a communication in its own right. Use the notice template that accompanies this register, and then log the notice here.
This template is general guidance on the standard NEC3 and NEC4 forms, not legal advice. It does not read your contract, so check it against your own contract including any Z clauses. NEC is a registered trade mark of its owner; Clause 60 Limited is not affiliated with or endorsed by NEC.

## Register
Early Warning Register
Project: |  |  |  | Today:
The last 'Could affect' column (Contractor's total cost) is a ground on which the Contractor may give an early warning. Under NEC4 the Project Manager may raise it too.
Ref | Date notified | Notified by | Notice reference | Description of the matter | Could affect: total of the Prices | Could affect: Completion | Could affect: a Key Date | Could affect: performance of the works in use | Could affect: Contractor's total cost | Early warning meeting date | Decisions and actions agreed | Action owner | Action due | Status | Date closed | Days open | Days left for action | Linked compensation event ref | Notes
EW-001 (example) | 2026-09-07 | Contractor | EWN-001 | Example only: utility records show a water main crossing the line of the new drainage run. Position and depth not confirmed. | X | X |  |  |  | 2026-09-10 | Trial holes to confirm position. Project Manager to ask the utility owner for records. Review at next meeting. | Contractor (site engineer) | 2026-09-24 | Open |  |  |  |  | Example row. Overwrite or clear the yellow cells.